## Sheet1
19.15%
152810
4584.3
| 157394.3 | 9443.658
| 34626.746 | 147950.642
| 122767.554 | 32549.1412 |  | 29216 | 23372.8
| 10230.6295 | 115401.5008 |  | 8764.8 | 16360.96
| 10230.6295 | 9616.7917 |  | 20451.2
4808.3959
31478.86
188873.16

## Sheet2
Phase | Task ID | Task Description | Sub-Task Details | Output / Deliverable
Phase 1 – Data Intake & Assessment | 1.1 | Identify all manual IAM data sources | HR headcount, IAM extracts, AD groups, app access, shared drives | Source inventory list
Phase 1 – Data Intake & Assessment | 1.2 | Collect HR headcount data | BRID, employee ID, cost center, department, role | HR master dataset
Phase 1 – Data Intake & Assessment | 1.3 | Collect manual application access data | User–app–permission extracts | Raw app access files
Phase 1 – Data Intake & Assessment | 1.4 | Collect AD group membership data | User–AD group mappings | Raw AD group files
Phase 1 – Data Intake & Assessment | 1.5 | Collect shared drive access data | User–drive path mappings | Raw shared drive files
Phase 1 – Data Intake & Assessment | 1.6 | Perform initial data quality checks | Missing IDs, duplicates, format issues | Data quality report
Phase 1 – Data Intake & Assessment | 1.7 | Standardize identifiers | Normalize BRID, employee ID, cost center | Cleaned baseline dataset
Phase 2 – Persona & Cost Center Foundation | 2.1 | Identify persona sources | RBAC definitions, SME inputs, policy documents | Persona source catalog
Phase 2 – Persona & Cost Center Foundation | 2.2 | Define persona taxonomy | Persona name, description, risk tier | Persona master list
Phase 2 – Persona & Cost Center Foundation | 2.3 | Map personas to cost centers | One-to-many persona–cost center relationships | Persona–Cost Center mapping table
Phase 2 – Persona & Cost Center Foundation | 2.4 | Define persona-based app entitlements | Expected apps and permissions per persona | Persona app entitlement matrix
Phase 2 – Persona & Cost Center Foundation | 2.5 | Define persona-based AD group entitlements | Expected AD groups per persona | Persona AD group matrix
Phase 2 – Persona & Cost Center Foundation | 2.6 | Define persona-based shared drive access | Expected drive paths per persona | Persona shared drive matrix
Phase 2 – Persona & Cost Center Foundation | 2.7 | Document exception handling rules | Temporary access, dual roles, overrides | Exception handling rules
Phase 3 – IAM Automation Enablement | 3.1 | Design automated IAM ingestion architecture | Data flow from IAM → AWS | Solution architecture diagram
Phase 3 – IAM Automation Enablement | 3.2 | Configure automated IAM data extraction | Scheduled jobs / APIs | Automated IAM feeds
Phase 3 – IAM Automation Enablement | 3.3 | Land raw IAM data into AWS S3 | Partitioned raw data storage | S3 raw data buckets
Phase 3 – IAM Automation Enablement | 3.4 | Transform and normalize IAM data | Clean, deduplicate, standardize | Processed IAM datasets
Phase 3 – IAM Automation Enablement | 3.5 | Implement logging and audit trail | Ingestion timestamps, record counts | Audit logs
Phase 4 – Application Permission Analytics | 4.1 | Design app permission comparison logic | Should-Have vs Does-Have rules | Comparison logic document
Phase 4 – Application Permission Analytics | 4.2 | Normalize application and permission names | Case, synonyms, duplicates | Normalized app-permission mappings
Phase 4 – Application Permission Analytics | 4.3 | Develop app permission comparison script | Persona vs actual permissions | Comparison output dataset
Phase 4 – Application Permission Analytics | 4.4 | Generate horizontal app access view | User/persona/app summary | App summary table
Phase 4 – Application Permission Analytics | 4.5 | Generate vertical app access view | Permission-level mismatch details | App detailed table
Phase 4 – Application Permission Analytics | 4.6 | Flag missing and excess permissions | Policy and risk alignment | Permission deviation indicators
Phase 5 – AD Group Analytics | 5.1 | Design AD group normalization strategy | Group naming, nesting rules | AD normalization logic
Phase 5 – AD Group Analytics | 5.2 | Develop AD group comparison script | Expected vs actual group membership | AD group comparison dataset
Phase 5 – AD Group Analytics | 5.3 | Identify excess and missing AD groups | Privilege escalation risks | AD risk indicators
Phase 6 – Shared Drive Analytics | 6.1 | Define shared drive normalization rules | Path formatting, slash handling | Path normalization rules
Phase 6 – Shared Drive Analytics | 6.2 | Develop shared drive comparison script | Persona vs actual drive access | Shared drive comparison dataset
Phase 6 – Shared Drive Analytics | 6.3 | Identify overexposed shared drives | Data leakage risks | Shared drive risk indicators
Phase 7 – Data Consolidation & Risk Scoring | 7.1 | Merge app, AD, and shared drive outputs | Unified entitlement view | Consolidated IAM dataset
Phase 7 – Data Consolidation & Risk Scoring | 7.2 | Join HR, persona, and cost center data | Organizational context enriched dataset | Enriched IAM dataset
Phase 7 – Data Consolidation & Risk Scoring | 7.3 | Compute access deviation metrics | Missing, excess, critical access | Deviation metrics
Phase 7 – Data Consolidation & Risk Scoring | 7.4 | Derive risk and compliance scores | Persona deviation and policy risk | Risk score dataset
Phase 8 – AWS & Tableau Deployment | 8.1 | Prepare Tableau-ready data models | Fact and dimension tables | Tableau data model
Phase 8 – AWS & Tableau Deployment | 8.2 | Publish curated datasets to AWS | S3 / Redshift deployment | AWS production datasets
Phase 8 – AWS & Tableau Deployment | 8.3 | Develop Tableau dashboards | Executive, audit, operational views | Tableau dashboards
Phase 8 – AWS & Tableau Deployment | 8.4 | Configure refresh schedules and access | RBAC, refresh cadence | Automated Tableau refresh
Phase 9 – Automation & Governance | 9.1 | Schedule end-to-end pipeline | Automated ingestion to reporting | Scheduled pipeline
Phase 9 – Automation & Governance | 9.2 | Implement data quality monitoring | Volume, drift, anomalies | Data quality dashboards
Phase 9 – Automation & Governance | 9.3 | Enable audit and compliance reporting | Evidence-ready outputs | Audit-ready reports